## Initial Discovery (hidden)
Company Overview
Tell us about your company. | GRO: Were a CBD hydroponics/gardening equipment (Hybrid) retailor.
Functionality Goals
How many products will the website/apps launch with? | the ecommerce side of the app/web will have 2-3000 products available for purchase.but our main focus is selling the entire rooms as a packages utilizing questionnaire to extract data, to formulate a recommendation, also our monthly subscription is a very important feature and the installation of the rooms themselves. streamlining the entire process for our customers.
Will the website/app offer free shipping? If not, how would you like the website to calculate shipping costs? | yes, free drop shipping at their home. with a minimum purchase order
Who is your credit card payment processor (example: authorize.net)? What forms of payments will you accept on the website? | Processor undecided at this time... looking to take most all forms of payment. CC, DEBIT all carriers, paypal money order
How many product categories will your website/app have? Any sub-categories? List all. | 2-3,000 items expected. From 4,500 listed on our partners site in addition to our full grow room packages
What is the price range of your products/services? | 5 dollars to 5,000 for individual products. 5k-15k full GrowRoom kits, 499-999 for installation, 99-199 for monthly subscription
Provide a detailed summary regarding your subscription services. What are the options? What do they cost? What services are provided? | 99/monthly paid annual subscription. 199/monthly paid monthly. full access to our technology, educational tools, and direct access to our growmasters
Will all products be coming from Hydrofarm? | Yes all products sold are manufactured by HydroFarm or purchased through hydrofarm channels
What product variations will be available? (color, size, etc) | multiple variations
What information is needed on your product details page? Here is what hydrofarm has: https://www.hydrofarm.com/p/category-led-lighting/photobio-m-led/ptb7600ls4 | similar to hydrfram on the ecommerce side of the things. but our recommended grow kits are the focus as well as our subscription.
Would you like to display a list of brands like this? https://www.hydrofarm.com/Our-Brands | Yes but not many .. we focus on our own GrowKit brands more. and list selected paid branding for outside brands we carry
Will products have multiple images? If so, how many max? | yes perhaps 3-4 images to view on some selected items especially and maybe more for our full grow room kits
Do you want customers to be able to leave product reviews? | grow room kit reviews subscription reviews, service reviews
What specific data would you like the website/apps to collect? (ex: GrowLOG data, etc) | Growlog data- Customer date-location-product data, ect
Here are the 4 main users of the website/app. Please describe their role and capabilities: -Administrative/Super-Admin -Retailers -Agents -Customers / - and paid subscription members different access to pricing and services | -Administrative/Super-Admin- backend tracking,logistics,sales,scheduling cross referencing crm -Retailers-different log into and face to the app for their team full access -Agents- are our sales force/technicians to have access to the products sold to their customers to the sales they made only -Customers ecommerce/ - and paid subscription members different access to pricing and services
Website and apps will include AI functionality that can be used to create a responsive relationship with the customer, such as automatically contacting the user when they need a product refill, learning when to upsell the user on certain products and keeping track of overall product inventory. Provide the specific AI functions needed. | locating the prospect and in conversion and the nurturing of the relationship with our paid customers.
Provide specific details for this: Includes a Life cycle of grow from inception to harvest. This life cycle trail is there for the user to be able to see what should be transpiring with their grow on a weekly basis. Similar applications to reference .. "WHAT TO EXPECT" when expecting. | the growlog function and the grow cycle function will basically go hand in hand. In the growlog this is a free service for all to use globally. this service for us a large data collection point. our paid subscription holder, once installation of their growroom is complete we help set them up on our technologies/APP to stay with them as they begin their grow journey. When they set up the app they will input their start date that will initiate they life cycle we put them on ... for example if they start their grow project on 11/11/20 from a seed we know to start the cycle start date they need starting from 11/11/20 from a seed formation ... so based on those 2 main factors we can start that customer on one of our cycles based on their start date and the type of growroom they have and whether begin from seed or clone. We then have weekly information or videos that will share important information and things to look for in that week or fast forwarding to the things to expect in the coming weeks... If the clients sees an issue that isn't lining up with what should be happening they will have direct contact with our growmaster to diagnose and remedy the issue. The growmaster will turn to the growlog for important information on what they have logged in the past and what the issue is to come us with the remedy. Both systems go hand in hand
Are you referring to standard live chat tools, like Drift.com for this? Direct contact methods for our users to communicate with our team. Instant messages text, photo, video sharing as well as live. This gives us the ability to diagnose issues with our clients grows over a digital platform. Similar features used on apps like. Doctor on demand. This function will be provided using third party communication tools and Dotlogics will provide recommendations on which to use. | in viewing drift.com yes some of the functionality they offer is part of what were looking for with more live feed communication like doctor on demand to be able to communicate and diagnose the issues in real time
Describe in more detail. Will the admin enter two prices for every product? One for logged-in customers and one for non-logged in customers? This feature will have blackout features that only paying customers can utilize. | yes that is correct. our paying subscription customers of the monthly service will get better pricing than a non subscription member only on our site to purchase products.
5. What variations are there for products?
6. What filters are on the product list page?
7. What details are available on the product details page?

## MP GX
Page | Designs | Status | TA's Suppositions for timeline | HTML | Development | Date | Designs | HTML | Development | Content Entered? | DL Reviewed? | QA | Client Approved?
Approved DL to Review TD to review Waiting on Client
Homepage | http://74.208.175.199/html-preview/GX/batch-2/a-homepage/design01.html |  |  | Done
How it works | http://74.208.175.199/html-preview/GX/batch-2/b-content/design01.html |  |  | Done
Features | http://74.208.175.199/html-preview/GX/batch-2/b-content/design02.html
Pricing > Choose Plan | http://74.208.175.199/html-preview/GX/batch-2/c-pricing/design01.html
Pricing > Login | http://74.208.175.199/html-preview/GX/batch-2/f-myaccount/01-auth/design01.html
Pricing > Choose Kit | http://74.208.175.199/html-preview/GX/batch-2/c-pricing/design02.html
Checkout > Billing Address | http://74.208.175.199/html-preview/GX/batch-2/d-cart/design01.html
Checkout > Shipping Address | http://74.208.175.199/html-preview/GX/batch-2/d-cart/design02.html
Checkout > Payment + Order Review | http://74.208.175.199/html-preview/GX/batch-2/d-cart/design03.html
Checkout > Thank You | http://74.208.175.199/html-preview/GX/batch-2/d-cart/design08.html
Pricing > Cart (Kit already purchased) | http://74.208.175.199/html-preview/GX/batch-2/d-cart-02/design01.html
Pricing > Login | http://74.208.175.199/html-preview/GX/batch-2/f-myaccount/01-auth/design01.html
Checkout > Payment + Order Review (Kit already purchased) | http://74.208.175.199/html-preview/GX/batch-2/d-cart-02/design02.htmll
Blog > Listing | http://74.208.175.199/html-preview/GX/batch-2/g-blog/design01.html |  | Approved (May have Minor changes) | Done
Blog > Detail | http://74.208.175.199/html-preview/GX/batch-2/g-blog/design02.htmll |  | Approved (May have Minor changes) | Done
Shipping Info | http://74.208.175.199/html-preview/GX/batch-2/e-info-pages/design01.html |  |  | Done
Privacy Policy | http://74.208.175.199/html-preview/GX/batch-2/e-info-pages/design02.html |  |  | Done
Terms and Condition | http://74.208.175.199/html-preview/GX/batch-2/e-info-pages/design03.html |  |  | Done
Contact Us | http://74.208.175.199/html-preview/GX/batch-2/e-info-pages/design04.html |  |  | Done
About Us | http://74.208.175.199/html-preview/GX/batch-2/e-info-pages/design05.html
FAQs |  |  | Same as HG | Based on design
Returns | Same as Privacy Policy |  | Approved (May have Minor changes) | Done
Why Us |  |  |  | Based on design
Guides |  |  |  | Based on design
My Account > Log In | http://74.208.175.199/html-preview/GX/batch-2/f-myaccount/01-auth/design01.html
My Account > Forgot Password | http://74.208.175.199/html-preview/GX/batch-2/f-myaccount/01-auth/design02.htmll
My Account > Reset Password | http://74.208.175.199/html-preview/GX/batch-2/f-myaccount/01-auth/design03.html
My Account > Register | http://74.208.175.199/html-preview/GX/batch-2/f-myaccount/01-auth/design04.html
My Account > Profile (Option 01) | http://74.208.175.199/html-preview/GX/batch-2/f-myaccount/09-my-profile-options/design01.html
My Account > Profile (Option 02) | http://74.208.175.199/html-preview/GX/batch-2/f-myaccount/09-my-profile-options/design02.html
My Account > Profile (Option 03) | http://74.208.175.199/html-preview/GX/batch-2/f-myaccount/09-my-profile-options/design03.html
My Account > Profile (Option 04) | http://74.208.175.199/html-preview/GX/batch-2/f-myaccount/09-my-profile-options/design04.html
My Account > Profile | http://74.208.175.199/html-preview/GX/batch-2/f-myaccount/02-my-dashboard/design01.html
My Account > Change Password | http://74.208.175.199/html-preview/GX/batch-2/f-myaccount/02-my-dashboard/design02.html
My Account > Addresses | http://74.208.175.199/html-preview/GX/batch-2/f-myaccount/03-my-addresses/design01.html
My Account > Addresses > Add New | http://74.208.175.199/html-preview/GX/batch-2/f-myaccount/03-my-addresses/design02.htmll
My Account > Addresses > Edit | http://74.208.175.199/html-preview/GX/batch-2/f-myaccount/03-my-addresses/design03.html
My Account > Payments | http://74.208.175.199/html-preview/GX/batch-2/f-myaccount/04-my-payments/design01.html
My Account > Payments > Add | http://74.208.175.199/html-preview/GX/batch-2/f-myaccount/04-my-payments/design02.html
My Account > Billing > Listing | http://74.208.175.199/html-preview/GX/batch-2/f-myaccount/05-billing/design01.html
My Account > Billing > Details (Subscription) | http://74.208.175.199/html-preview/GX/batch-2/f-myaccount/05-billing/design02.html
My Account > Billing > Details (Kit) | http://74.208.175.199/html-preview/GX/batch-2/f-myaccount/05-billing/design03.html
My Account > My GrowLog | http://74.208.175.199/html-preview/GX/batch-2/f-myaccount/06-my-grow-log/design01.html
My Account > My GrowLog > Additional Information | http://74.208.175.199/html-preview/GX/batch-2/f-myaccount/06-my-grow-log/design02.html
My Account > My GrowLog > View Grow Log | http://74.208.175.199/html-preview/GX/batch-2/f-myaccount/06-my-grow-log/design03.html
My Account > My GrowLog > Preview | http://74.208.175.199/html-preview/GX/batch-2/f-myaccount/06-my-grow-log/design04.html
My Account > My GrowLog > Add/Edit | http://74.208.175.199/html-preview/GX/batch-2/f-myaccount/06-my-grow-log/design05.html
My Account > My Grow Tracker | http://74.208.175.199/html-preview/GX/batch-2/f-myaccount/07-my-grow-tracker/design01.html
My Account > My GrowMaster | http://74.208.175.199/html-preview/GX/batch-2/f-myaccount/08-my-grow-master/design01.html

## MP HGP
Page | Designs | HTML | Development | Date | Designs | HTML | Development | Content Entered? | DL Reviewed? | QA | Client Approved?
Approved DL to Review TD to review Waiting on Client
Homepage | http://74.208.175.199/html-preview/HGP/batch-3/a-homepage/design01.html | Done
About Us | http://74.208.175.199/html-preview/HGP/batch-3/b-content/design01.html | Done
FAQ's | http://74.208.175.199/html-preview/HGP/batch-3/b-content/design02.html | Done
How It Works | http://74.208.175.199/html-preview/HGP/batch-3/b-content/design03.html | Done
Pricing | http://74.208.175.199/html-preview/HGP/batch-3/c-pricing/design01.html
Homepage > Pricing Link Added | http://74.208.175.199/html-preview/HGP/batch-3/c-pricing/design01.html | Done
Pricing Detail | http://74.208.175.199/html-preview/HGP/batch-3/c-pricing/design02.htmll | Done

## Product File (hidden)
Name* | Detail* | Categories | Subcategories | Hydrofarm Brand | Status | Price* | Sales Price | Sales Price Start | Sales Price End | SKU | Stock Availability (In Stock / Out of Stock) | Base Image | Additional Images | Meta Title - 60 characters | Meta Description- max 160 characters | Certification Mark | Attribute i.e size | Values i.e red | Related Documents | Related Products
http://prntscr.com/tr36c6 | http://prntscr.com/tr36s7 | http://prntscr.com/tr37kp | http://prntscr.com/tr37kp | http://prntscr.com/tr391c | admin side field | admin side field | http://prntscr.com/tr39rd | admin side field | admin side field | http://prntscr.com/tr39f2 | admin side field | http://prntscr.com/tr3b05 | http://prntscr.com/tr3bdn | admin side field | admin side field | http://prntscr.com/tr3ggo | http://prntscr.com/tr3qk8 | http://prntscr.com/tr3rgj | http://prntscr.com/tr3hz4 | http://prntscr.com/tr3ijr
Phantom 50 Series, DE Open Lighting System, 1000W, 208V/240V |  | Lighting | Lighting Systems/Kits | Phantom DE |  |  | 448.99 |  |  | PHDEOK11 |  | https://www.hydrofarm.com/DesktopModules/Revindex.Dnn.RevindexStorefront/Portals/0/Gallery/23171146-69a5-4516-8c2f-d889dcfb7689.jpg | https://www.hydrofarm.com/p/category-lighting-systemskits/phantom-50-series-de-open-lighting-system/phdeok11#, https://www.hydrofarm.com/p/category-lighting-systemskits/phantom-50-series-de-open-lighting-system/phdeok11#, https://www.hydrofarm.com/p/category-lighting-systemskits/phantom-50-series-de-open-lighting-system/phdeok11#, https://www.hydrofarm.com/p/category-lighting-systemskits/phantom-50-series-de-open-lighting-system/phdeok11# | [6 empty] | Phantom 50 Series Truss Hangers, Set of 2

## Third-Parties
Third-Parties | Recommended Plan | Comments | Account credentials
Algolia | Starter plan: https://www.algolia.com/pricing/ |  | NO
Drift | Free plan: https://www.algolia.com/pricing/ |  | NO
Agora.io: Video Calling
Mailchimp | Standard Plan: https://mailchimp.com/pricing/ | Standard Plan | Yes
Calendly | ? Plan: https://calendly.com/pages/pricing | We never worked on this so currently we unable to recommend plan | Yes
Avalara Tax management | Create account https://www.avalara.com/us/en/index.html |  | NO
Google analytics | Create Account: analytics.google.com |  | Yes
Braintree: Payment processing | Create Account: https://www.braintreepayments.com/ |  | NO
PayPal: Payment processing | Create Account: https://www.paypal.com/bizsignup/#/checkAccount |  | Yes
Hotjar | https://www.getapp.com/business-intelligence-analytics-software/a/hotjar/pricing/ |  | NO
AWS: Hosting | Create account: Server specs: t3a.large vCPU :2 Memory 8 GiB |  | NO

## GX Qsheet
Status | Q | Reference | Screenshot
PC= Pending Client TD: Pending TD DL: Pending DL HY: Hydrofarm
Hydrofarm | We need a tech person from Hydrofarm to answer any technology related questions we have.
Hydrofarm | How will product data be given to us?
Hydrofarm | How often does product data change? Ex: pricing.
Hydrofarm | On call, Hydrofarm talked about gaining "insights" and customer data. What specifically are they looking for?
If all products are coming directly from Hydrofarm, do we need any editing/management capability on our two websites for products and categories?
Do you need to be able to edit pricing on the HGP website or will pricing come directly from Hydrofarm?
TA | Do monthly subscriptions auto-renew? How do I as the customer, cancel? At what point would a customer ever want to cancel?
Describe these sheets. A video would be great. https://prnt.sc/t7n8kz
TA | When a customer opens his/her GrowLog, what info do they need to fill out? Provide a list of specific questions. Are all of the questions mandatory.
TA | can agents connect directly with customer? How will customers sign up if coming through a retailer. | Will be answered in spec document.
TA | Where customers can subscribe? | Will be answered in spec document.
What is the process: Who assigns a GrowMaster to a customer? Who assigns the GrowTech and GroPro to a customer
TA/AT | Upon login, the GrowMaster will see: -his/her basic profile -the name of the customer, his/her contact info and when they subscribed. -the customers grow log. -the retailer (if customer came via retailer) -the growpro for the account with his/her name and contact info. -the grotech for the account with his/her name and contact info. - in order to see all messages and communication between the growtec and the customer, GrowMaster will have to login to the specific growtech/growpros account (we'll be using Zendesk or other solution for messaging, ticketing and support).
Upon login, the retailer will see: -his/her basic profile -the name of the customer, his/her contact info and when they subscribed. -the customers grow log.
The GrowPro and GrowTech will see: -his/her basic profile -the name of the customer, his/her contact info and when they subscribed. -the customers grow log. -the retailer (if customer came via retailer) - all messages and communication between this growtech/growpro and the customer (we'll be using Zendesk or other solution for messaging, ticketing and support). "
TD: I need to know what solution you want to offer so that customers and growpros can communicate. How will that integrate with our design interface? What functions will be available?
TA | do retailers have to select categories while signing up? | Not sure I understand the question.
TA | On what basis system will formulate a recommendation of specialist? | Admin to do manually. Will be answered in spec document.
TA | What is the shipping cost to customers? Free shipping? Is there an order minimum, if so, what amount?
Once a purchase is made on HGP, do we send an email notification to hydrofarm? How do we notify them?
Once a subscriber joins growX, does Hydro need to be notified at all?
HS | Once a customer subscribes to grow X, what happens? They login...and?
TA | what do you meant by room packages? | growkit
AT | On HGP, when a user is at the end of the shopping cycle, they'll be asked to speak to a GrowPro so that a sales pitch can be made to sign-up to GrowX. My recommendation is to have an open calendar so if someone selects the same date and time as another, they should be able to do so. You, the admin would have to have people available to take those two calls, scheduled for the same time. Please confirm if that is how you envision the calendar. | if needed then 3rd part app is the solution
AT | what should be displayed without login | Will be answered in spec document.
AT | Specialist will not visit second time any way? | Does not have anything to do with our website.
HS | For the GrowTeam, do we need to know any specifics like: Date of when he/she visited the customers house? What else is needed?
AT | monthly subscrption and grow is for 4 months. So will customer subscribe each month? | HS: infinite time frame, ongoing log until close via button
HS | How do I cancel a subcription? What are the subscription tiers and prices? What is the difference in each?
AT | where amount is added for retailer to use specailist? | i guess customers by subscription on that basis he will get specialist. HS: no charge for retailers for now
AH | Agent - Retailer (Retailer will sign-up for monthly subscription to growx platform?) Same like if someone say ok purchase pur product if need maintaince and support contact to our partners same concept applies here retailer will sign on growx and he will refer (not refer actually) his customers to growx planting team and they will visit that custome and the all the process will be carried out. | Sounds correct, yes.
AH | a) Retailer customers sign up for subscription on retailer website or off site?. How will customer and retailer will be linked? | Will be answered in spec document.
What are the possible room sizes?
Tell us specifics about the "kits". How many possible kits are there on the website? Everything else is a singluar product, correct?
AH | What are the questions the customer should see in order to "Get your estimated GrowSpace"?
AH | If a customer does not regularly fill out the weekly GrowLog, what happens?
AH | Does the growlog have an expiration date? Can customers delete the entire log? Can customers create a new log, even though they already have one? | goes on infinitly. for that specific harvest.
RR | Provide the payment gateway we'll use on both sites. Authorize.net or other
RR | TD - will the apps work offline? What will or will not work.
TD: we want to collect user generated data and analytics. Like: when will the customers products finish, we should send him an email. What other triggers and similar alerts can we create to keep the customer engaged AND to learn more about the customer. Like: which retailer has the most subscribers -what percentage of customers buy a kit vs a single product -what percentage of customers buy from HGP AND are subscribers on GX?
How to have ONE customer account on both sites?
Which in-app notifications to show?

## Backlog HGP (hidden)
Sprint # | Deliverables | Assign to | Sprint # | Estimation | Deliverables | Assign to | Estimation (hours) | Sprint # | Deliverables | Assign to | Estimation
| Adminside |  |  |  | Frontside |  |  |  | Third Party Integration
Algolia
| homepage | Rashid |  | 2 | Homepage | Rameez | 3 |  | Drift
| Customers | Rashid |  | 2
| Brands | Usman |  | 1 | Navigation Structure | Rameez | 2 |  | calendly.com
| Products listing | Usman |  | 1 | Subscribe to Newsletter | Rameez | 1 |  | Mailchimp
| Products categories | Usman |  | 1
| Product Detail: Attributes, Related products, Product Images, Product Whole Sale Prices, Product Bar Codes, Product Dimensions, UOM Conversions, Inventories (listing of product inventory by distributon center) Product Family | Usman |  | 12 | Register (Same for HG & GX) | Rameez | 2
| Integration of Products API | Usman |  | 8 | Login | Rameez | 2
| Integration of Categories API | Usman |  | 3 | Forgot Password | Rameez | 2
| Set Cron job for Products | Usman |  | 2
| Set Cron job for Categories | Usman |  | 2 | My Account
| Cart APIs Add to cart Add addon as a product Change Quantity Remove item Billing & Shipping Merge cart against customer | Usman |  | 8 | Profile | Rameez | 1
| Admin Pages + APIs Terms & Conditions Privacy Policy Contact Us About Us Who we are Support | Rashid |  | 8 | Billing addresses --> Add ¦ Edit ¦ Delete ¦ List | Rameez | 3
| Blog + API | Rashid |  | 2
| Payment Gateway | Usman |  | 3
| Coupons + API | Usman |  | 4 | Wishlist --> List ¦ Delete ¦ Add to Cart | Rameez | 2
| News listing / Detail + API | Rashid |  | 2 | Payment options --> Add ¦ Delete | Rameez | 4
| Reports |  |  |  | Order history --> List ¦Search & Sort ¦ Detail | Rameez | 3
| Orders (Admin) Order Listing Order status & tracking info change using Cron | Rashid |  | 4 | Change password (common practice) | Rameez | 1
| Profile Update API | Rashid |  | 1
| Change Password API | Rashid |  | 1 | Product Listing
| Orders (listing/detail) API | Usman |  | 3 | Listing (Associated with main or sub category) | Rameez | 3
| Payments (Add/Edit/Delete) API | Rashid |  | 4 | Add to Wishlist | Rameez | 1
| Address Book (Add/Edit/Delete) API | Rashid |  | 3 | Add to Cart | Rameez | 1
| Rating & Review | Usman |  |  | Product Detail |  | 4
[5 empty] | Increase/descrease Quantity | Rameez | 2
[5 empty] | Speak to a Grow Specialist (calendly) | Rameez
[5 empty] | Tab for Product Details | Rameez | 1
[5 empty] | Tab for Specifications (two-column table) | Rameez | 1
[5 empty] | Tab for Additional Information (PDFs, if applicable) | Rameez | 1
[5 empty] | Rrelated item | Rameez
View Cart (Merge Cart)
[5 empty] | Remove product from cart | Rameez | 1
[5 empty] | Increase/descrease Quantity | Rameez | 2
Checkout (Guest or Register)
[5 empty] | enter/review contact | Rameez | 2
[5 empty] | Shipping Address | Rameez | 2
[5 empty] | Billing Address | Rameez | 1
[5 empty] | Payment information (VISA, MC, AMEX, or PayPal) | Rameez | 4
[5 empty] | Order Confirmation | Rameez | 1
[5 empty] | Thank You Page | Rameez | 1
[5 empty] | option to schedule their GrowTeam consultation (calendly) | Rameez
CMS
[5 empty] | About Us | Rashid | 1
[5 empty] | How it Works | Rashid | 1
[5 empty] | Help - Contact Us (submit to the admin & default response) - FAQs | Rashid | 2
[5 empty] | Shipping | Rashid | 1
[5 empty] | Returns | Rashid | 1
[5 empty] | Terms and Conditions | Rashid | 1
Blog
[5 empty] | Listing | Rashid | 1
[5 empty] | Detail | Rashid | 2
[5 empty] | Site Search (Algolia) | Rameez | 4
Email Triggers
[5 empty] | Abandoned cart | Usman | 5
[5 empty] | New account registration | Rashid | 1
[5 empty] | New order | Rashid | 1
[5 empty] | Password reset request | Rameez | 1
[5 empty] | Admin uploads order tracking number | Rameez | 1
[5 empty] | A user purchases one of the three GrowKits/GrowRooms | Rameez | 1

## Backlog GX (hidden)
Sprint # | Deliverables | Assign to | Sprint # | Estimation | Deliverables | Assign to | Estimation (hours) | Sprint # | Deliverables | Assign to | Estimation
| Adminside |  |  |  | Frontside |  |  |  | Third Party Integration
[9 empty] | Mailchimp |  | 1
| Admin - Homepage + API | RB |  | 2 | Homepage | RB | 2 |  | chat / comet chat
| Admin - User management |  |  |  | Navigation Structure | RB | 1
| Admin users Add ¦ Edit ¦ Delete ¦ List | RB |  | 2 | Subscribe to Newsletter | RB | 1
| Customers Add ¦ Edit ¦ Delete Retailers Add ¦ Edit ¦ Delete ¦ List | UI |  | 2 |  | RB | 2
| Register GrowMaster + Register as agent in cometchat |  |  |  | Instagram Feed
Pricing Edit ¦ List
[5 empty] | Register (Same for HG & GX) | RR | 1
| Blog + API | RB |  | 2 | Login | RR | 1
| Payment Gateway integration + API | UI |  | 4 | Forgot Password | RR | 1
[5 empty] | Reset Password | RR | 1
Dependant on subscription | Orders (Admin) Order Listing Order Detail | UI |  | 6 | My Account
| Profile Update API | RB |  | 2 | My Profile | RR | 2
| Change Password API | RB |  | 1 | Billing addresses --> Add ¦ Edit ¦ Delete ¦ List Admin will check the legal states for cannabis | RR | 2
| Orders (listing/detail) API | UI |  | 4 | Payment options --> Add ¦ Delete | RR | 3
| Payments (Add/Edit/Delete) API | RB |  | 2 | My Order --> Monthly subscription details, and selected payment type | RR | 2 | approx
| Address Book (Add/Edit/Delete) API | RB |  | 1 | Change password (common practice) | RR | 1
My GrowLog (Only one active) ----- growing tools
| GrowMaster/GrowPro/GroTech Dashboard |  |  |  | - Harvest Date
| - List of customers who subscribed and assigned to me |  |  |  | - Active/Inactive log
- Weekly GrowLog to review & monitor
| - Provide feedback on customer logs |  |  |  | CMS
| - Respond to support tickets, messages and live chat |  |  |  | About Us | RB | 2
| - Retailers list |  |  |  | How it Works | RB | 2
issue | - Customers list (retailer if apllicable) | UI |  | 2 | - FAQs | RB | 2
[5 empty] | - Contact Us (submit to the admin & default response) | RB | 2
| Retailer Dashboard |  |  |  | Shipping | RB | 1
| - add their customers (name, email address, and GrowKit purchased) Add ¦ Edit ¦ Delete | RR |  | 3 | Returns | RB | 1
| - Customer list | RR |  | 2 | Terms and Conditions | RR | 1
| Cutomer detail - basic profile information , - - GrowKit purchased -date of when they subscribed | RR |  | 3 | Why Us | RR | 1
[5 empty] | Guides | RR | 1
| Growlogs |  |  |  | Support | RR | 1
| Settings |  |  | 1 | Pricing
Feature
Admin Pages + APIs
Blog
| Reports TBD |  |  |  | Listing | RB | 1
[5 empty] | Detail | RB | 2
| Ticketing system. |  |  | 39
| RR | 24
| UI | 18 |  |  | Site Search (Algolia) | RR | 3
| RB | 34
Email Triggers TBD
[5 empty] | New account registration (when retailer add his customer) user will get link to set up password | UI | 1
[5 empty] | Registration confirmation email | RB | 1
[5 empty] | Forgot password - if a customer requests a new password | RB | 1
[5 empty] | Order confirmation email to customers when they subscribe | UI | 3
[5 empty] | Order confirmation for admin | UI | 1
[5 empty] | Order tracking email if customer purchases a kit | UI | 1
[5 empty] | Admin to assign Grow Master to customer | UI | 2
[5 empty] | A user purchases one of the three GrowKits/GrowRooms | UI | 2
My GrowTracker ----- growing tools
- tutorial information - File system
Your GrowMaster ----- growing tools
- 3rd Part messaging system - cometchat
- Ticketing system.
Subscribe to GrowX
- Select a GrowKit (User can skip the step)
- (Login required)
- Select the monthly or yearly membership
- Shipping Address
- Billing Address
- Payment information (VISA, MC, AMEX, or PayPal)
- Order Confirmation
- Thank You Page
=> short video tutorial about the GrowX dashboard - First-time customers
=> redirected to their internal dashboard

## Backlog GX II
Sprint # | Deliverables | Assign to | Sprint # | Estimation | Deliverables | Assign to | Estimation (hours) | Sprint # | Deliverables | Assign to | Estimation
| Adminside |  |  |  | Frontside |  |  |  | Third Party Integration
[9 empty] | Mailchimp |  | 1
| Admin - User management |  |  |  | Homepage | RB | 2 |  | chat / comet chat
| Register GrowMaster + Register as agent in cometchat | RR |  | 2 | - Instagram Feed
My Account
| Pricing Edit ¦ List | UI |  | 2 | My Order --> Monthly subscription details, and selected payment type | RB | 2
| Payment Gateway integration + API | RB |  | 4
[5 empty] | My GrowLog (Only one active) ----- growing tools |  | RR | 4
| Orders (Admin) Order Listing Order Detail | UI |  | 5 | - Harvest Date |  | RR
| Orders (listing/detail) API | UI |  | 1 | - Add ¦ Inactive log |  | RB | 2
[5 empty] | - View ¦ edit |  | RB | 4
| GrowMaster/GrowPro/GroTech Dashboard |  |  |  | - Weekly growlog updates |  | RR | 2
Dependant on subscription | - List of customers who subscribed and assigned to me | UI |  | 2
| - Weekly GrowLog to review & monitor | RR |  | 3 | CMS
| - Provide feedback on customer logs | RR |  | 3 | About Us |  | RB | 2
| - Respond to support tickets, messages and live chat |  |  |  | - FAQs |  | RB | 1
| - Customers list (retailer if apllicable) | UI |  | 2 | Why Us |  | RB | 1
[5 empty] | Guides |  | RB | 1
| Retailer Dashboard |  |  |  | Support |  | RB | 1
| - customers (GrowKit purchased) | UI |  | 1 | Pricing |  | RB | 2
| Cutomer detail - basic profile information , - - GrowKit purchased -date of when they subscribed | UI |  | 1 | Feature |  | RB | 2
| Growlogs | RR |  | 2 | Site Search (Algolia)
Email Triggers TBD
| Reports TBD |  |  |  | Order confirmation email to customers when they subscribe |  | UI | 1
[5 empty] | Order confirmation for admin |  | UI | 1
| Ticketing system. |  |  |  | Order tracking email if customer purchases a kit |  | UI | 2
| https://prnt.sc/us6dk8 |  |  |  | Admin to assign Grow Master to customer |  | UI
| Legal states |  |  |  | A user purchases one of the three GrowKits/GrowRooms |  | UI | 4
| Admin will check the legal states for cannabis | RB |  | 2
| - tutorial information - File system | RR |  | 3 | My GrowTracker ----- growing tools
[5 empty] | - tutorial information - File system |  | RR | 3
Your GrowMaster ----- growing tools
- 3rd Part messaging system - cometchat
| RR | 40 |  | 33 | - Ticketing system. |  | RB | 12
| UI | 16 |  | 22 | Subscribe to GrowX
| RB | 22 |  | 38 | - Select a GrowKit (User can skip the step) |  | RR | 1
| Total | 88 |  | 93 | - (Login required) |  | RR | 1
| Planned sprint | 78 |  |  | - Select the monthly or yearly membership |  | RR | 2
[5 empty] | - Shipping Address |  | RR | 2
[5 empty] | - Billing Address |  | RR | 1
[5 empty] | - Payment information (VISA, MC, AMEX, or PayPal) |  | RR | 4
[5 empty] | - Order Confirmation |  | RR | 2
[5 empty] | - Thank You Page |  | RR | 1
=> short video tutorial about the GrowX dashboard - First-time customers
=> redirected to their internal dashboard

## HGP-Feedback (hidden)
Sr# | Questions/Changes | Concerned Person | Reply/Status
Jing : https://drive.google.com/file/d/1sT1-8ilwlnlthRvg11PHy4TAV8spGz-9/view
1 | How is search going to be work? (0:00 - 0:43 ) | RR | We have used algolia for searching, we can search products and blogs. Testing account was used for now.
2 | Need hover effect for Featured products on homepage (0:44 - 1:22) | AR | QA : 7-9-2020 3:41pm Done Reference: https://drive.google.com/file/d/1DBMNbZmjkFZrV6NqjknUkP650LgrJjzC/view
3 | Need Effect for Packages section "Talk to Specialist" Button 1:23 - 2:10) see the effect on play button https://kingkong.com.au/ | AR | QA : 7-9-2020 3:45pm Done Reference: https://drive.google.com/file/d/1yRCSVCVmBRnWYcYxo5H0UjUO_QE8iBwS/view
4 | Is Brand filtering working fine? (2:11-2:53) | AT | Yes, it is working fine. It will show all the products containing the specific selected brand.
5 | How does pagination work? (2:54-3:13) | AT | Clicking on 'Discover More' button loads maximum 12 products. And Discover More button will appear until we reach to the total products count http://prntscr.com/ucz0nw
6 | Need an outline for Category and brand filters(3:14-3:50) | AR | QA: 7-9-2020 4:12 pm Done Reference : http://prntscr.com/ucyqnr http://prntscr.com/ucyr99
7 | Please move brand to the reviews place and remove color from the brand heading. (3:51-5:12) Brand: Category_Name | AR | QA: 7-9-2020 4:14 pm Done Reference : http://prntscr.com/ucytkc
8 | Move product reviews after the short description. (3:51-5:12) | AR | QA: 7-9-2020 4:16 pm Done Reference : http://prntscr.com/ucywht
9 | There should not be button for out of stock product , there should be a simple text in red color "OUT OF STOCK" or there can be an outline for the text but this should not be clickable (5:13-6:50) | AR | QA: 7-9-2020 5:09 pm Done Reference: https://drive.google.com/file/d/1VPatAfdbpK4gytUSQ5FNts_IyW34f5dR/view
10 | Why we are showing Out of Stock products? (5:55-6:20) | AH/TA | These products are coming from Hydroform. If we stop displaying the out of stock products, the quantity of active products will be very less. Out of stock products can added to wishlist so that when the product restocked user can purchase. How walmart handle their out of stock items https://www.walmart.com/ip/Linzer-BEST-Professional-Polyester-Paint-Brush-Set-2-Piece/55206520 - Items are still in listing - user can set alert about restock - add to wishlist | HS Question: Why Active products are very less? How many products are available ? How many products are out of stock? | There is total of 5000 products and 2019 have stock greater than 0. We have functionality to add product in wishlist.
11 | Is there any solution not to reload the page on selecting different options? 6:21-8:00) | RR | Done QA: 8-9-2020 4:27 pm Done https://drive.google.com/file/d/19dVRMaYVV6z__dMFa6nJheAbgAdX1_9f/view
12 | Remove Linkedin Icon from product detail page and add Youtube icon (8:00-8:10) | AR/RR | Those icon are for social media sharing, we can't share a product to the youtube. | HS Answer: Facbook, twitter and instagram would be my preference for social sharing. | We can not share products on Instagram either. I think there should be Pinterest instead.
13 | Login page in checkout: Please add submit button instead of Login and remove register button and replace it with text and make hyperlink. (8:10-8:45) | AR | QA: 7-9-2020 4:40 pm Done Reference: http://prntscr.com/uczc2j
14 | Please add Show Password option for password (8:46-9:15) | AR | QA: 7-9-2020 4:56 pm 'Show Password' icon added for Login Page: http://prntscr.com/ucznov Register Page :http://prntscr.com/uczphs Change Password: http://prntscr.com/uczpyi Login for Checkout: http://prntscr.com/uczs5d Reset Password: http://prntscr.com/ud051v
15 | Remove Company name field from every place of the site (9:16-9:34) (10:04-10:16) | RR | QA: 8-9-2020 Done Company name removed from : My profile: http://prntscr.com/udh63q My Addresses: http://prntscr.com/udh6fp Billing/Shipping : http://prntscr.com/udh6z4
16 | My Account--> Address should be ADDRESSES (9:35-9:55) | AR | QA: 7-9-2020 5:04 pm Done Reference: http://prntscr.com/uczssd
17 | Add new addresses --> Change 'Label as' to 'Nickname' (9:56 - 10:04) | AR | QA: 7-9-2020 5:12 pm Done http://prntscr.com/uczy4c
18 | My Account--> Payments : Change text to "No payment method found" (10:16-10:23) | AR | QA: 7-9-2020 5:15 pm Done http://prntscr.com/uczztf
19 | My Account--> Add Payment : Change text to "Add Payment Method" (10:23-10:31) | AR | QA: 7-9-2020 5:24 pm Done http://prntscr.com/ud07fc
20 | My Account--> Add Payment : Please Use a clear image for what's this(10:31-10:42) | AR | Image updated, Done QA: 8-9-2020 9:32 am Done Image replaced http://prntscr.com/uddz2e
21 | Test Account for reviewing My Account section(10:44-11:06) | AT | Credentials: Login: dotlogics1188@gmail.com Password: Hello12!
22 | Replace Grow word with Master Admin(11:08-11:13) | AT | QA: 7-9-2020 5:30 pm Done http://prntscr.com/ud0bhn
23 | Remove the bottom bar from admin side (11:13-11:16) | RR | QA: 8-9-2020 11:12 am Done https://prnt.sc/udf5yh
24 | Need an image for admin side with welcome text (11:16-11:41) | AR | QA: 8-9-2020 11:12 am Done http://prntscr.com/udfv6p
25 | Is there going to be any analytical thing on Admin dashboard? (11:41-11:55) | AH/TA | Sales analytics will be displayed http://prntscr.com/udioue
26 | Order of the admin tabs should be same like Shopify. Highest priority items should be on top and secondary items should be at bottom of the list.(11:56-13:36) | RR | QA: 8-9-2020 4:32 pm Done Highest priority items are now at the top of the list. http://prntscr.com/udlcc4
27 | Can we have a single tab/dropdown for Users,admins,roles and teams ? (13:36-14:33) | RR | QA: 8-9-2020 12:51 pm Done http://prntscr.com/udgxw5
28 | Make a Content Management tab and put "Edit home page" and "Blog" Section Under it.(14:34:15:34) | RR | QA: 8-9-2020 12:55 pm Done All Tabs related to content management has been moved under the CMS tab http://prntscr.com/udh0gn
29 | How can we differentiate between HG blogs and GX blog? | AH/TA | While adding particular content admin will have a dropdown. where he select an option: publish on (GX or HG) | HS Question: How would we differentiate between HG and GX data on listing page. | At listing page there will be a source column where admin can see which content belongs to which site. The source column on listing will display logo of the site see example http://prntscr.com/udflwh
30 | How can we differentiate between all data for HG and GX as we have same admin for both. for example Blogs,Orders,Users,Categories (15:41 -16:45) | AH/TA | While adding particular content admin will have a dropdown. where he select an option: publish on (GX or HG) | HS Question: How would we differentiate between HG and GX data on listing page. e.g Orders,Blogs,Users,Categories. | At listing page there will be a source column where admin can see which content belongs to which site. The source column on listing will display logo of the site see example http://prntscr.com/udflwh

## GX-Feedback
Sr# | Questions/Changes | Reply
1 | Change InActive to Inactive | InActive has been changed to Inactive Reference: http://prntscr.com/ups5mq
2 | There should not be a Password field while add a new User. | You are viewing the old screenshot. Password field is no more there( http://prntscr.com/ups73w ). Customers, Retailers and Grow Specialist can Set their password through the link sent in email. Reference Video: https://drive.google.com/file/d/1k79RYYypsVSBnidzIRi8N9y05khvAHV8/view
3 | Incomplete/Pending items: | 1.Currently Retailer can not see his customer's purchased kit. 2. Retailer can not add multiple users at once. 3. Retailer can not see date of customer's subscription. 4. Grow Specialist Dashboard is not developed yet.
4 | How to Create and Login GX Customer? | 1. Admin can create a GX customer from Admin Side-->User Management-->GX Customers--> Add New https://hgpadmin.dotlogicstest.design/admin/users/create?source=customers 2. GX Customer can set his/her password through the link sent to the email address provided by Admin. http://prntscr.com/upr0r7 3. GX Customer can login to the site from front end. Reference Video: https://drive.google.com/file/d/1k79RYYypsVSBnidzIRi8N9y05khvAHV8/view
5 | How to Create a Retailer and Login to Retailer's Dashboard? | 1. Admin Can Create a Retailer from Admin Side-->User Management-->Retailers-->Add New https://hgpadmin.dotlogicstest.design/admin/users/create?source=retailers 2. Retailer can set his/her password through the link sent to the email address provided by Admin. http://prntscr.com/upr0r7 3. Retailer can login to dashboard from admin side. Reference Video: https://drive.google.com/file/d/1ROBCoO2PmPo2_4yz9CqhQ-fmV-BGQ4aQ/view
6 | How to Create Retailer's Customers? | 1. Login to Retailer dashboard and add new customer from Customers-->Add new http://prntscr.com/upr9ri 2. Now follow the simple GX customer creation flow as mentioned above. http://prntscr.com/upradn 3. Retailer can add multiple users. Reference Video: https://drive.google.com/file/d/1sU6FS4WZCTkV9cv_FUl8ioMGpOhJdaNL/view
7 | How to Create Grow Master, Grow Pro and Grow Tech? | 1. Admin can create account for Grow Master, Grow Pro and Grow Tech from Admin side --> User Management --> Admins--> Add New https://hgpadmin.dotlogicstest.design/admin/users/create?source=admins 2. Grow Master, Grow Pro and Grow Tech can set their password through the link sent to the email address provided by Admin. http://prntscr.com/upr0r7 3. Grow Master, Grow Pro and Grow Tech can login from the admin side but currently their dashboard is not ready that's why the Dashboard is empty. Reference Videos: Grow Master: https://drive.google.com/file/d/1s_Edx9mehvSd-ZxSH_kTRuqfmV-UKROc/view Grow Pro: https://drive.google.com/file/d/1fA32XgPJpylm5pxSRTuIxLtNZ2EGrbKy/view Grow Tech: https://drive.google.com/file/d/1y7e7O89aBwmhCvRnqmyCFpuo2KONWdpS/view

## Open items
| Emails | Source | Screenshots | TD Replies
GX | Welcome email | Website |  | Need content
HGP + GX | Forgot password | Website | https://prnt.sc/uqki0h http://prntscr.com/uro2c5 | Received content
HGP + GX | Registration | Website | http://prntscr.com/uqlget http://prntscr.com/uro0sn | Received content
HGP | Order | Website | http://prntscr.com/uql43s | Received content
HGP | Contact Us User | Website | https://prnt.sc/uqkpgl http://prntscr.com/uro3bq | Received content
HGP | Contact Us Admin | Website | https://prnt.sc/uqks5f http://prntscr.com/uro2rm | Received content
HGP | Subscribe to Our Newsletter |  |  | Received content. Email is generated by Mail chimp that's why its template can not be changed.
HGP | Your Tracking Information |  |  | Received content. Tracking information functionality is not developed yet that's why its email is not generated yet.
HGP | Abandoned Cart |  |  | Received content. Email is generated by Mail chimp that's why its template can not be changed.
GX | Order confirmation for admin |  |  | Need content
GX | Order confirmation email to customers when they subscribe |  |  | Need content
GX | Order tracking email if customer purchases a kit |  |  | Need content
| 3rd parties | Implemented
HGP + GX | Algolia | No | Cilent to upgrade plan
HGP + GX | Mailchimp | Yes
HGP + GX | Calendly | Yes | Cilent to upgrade plan HS: Use free olan for now
HGP + GX | Avalara Tax management | No | Need account credentials
HGP + GX | Google analytics | Yes | Received
HGP + GX | PayPal: Payment processing | Yes | 2FA authentication needed
HGP + GX | Hotjar | No | Unable to login
HGP | Subscribe to our Newsletter | Yes |  | For HGP we are using HomeGrown Pros, Inc audience for newsletter subscription.
GX | Subscribe to our Newsletter | No |  | We are using HGP listname. if no then please ask client to add new audience list for that.
HGP + GX | Send Tracking information to the user upon receiving from hydrofarm API | No | Email trigger is pending
HGP + GX | Live chat | No | Need to purchase cometchat plan for integration. https://prnt.sc/uioqv4
GX | Need instagram app verification for instagram feed | No | https://prnt.sc/um85s1 https://prnt.sc/um862m
HGP + GX | AWS: Hosting
GX | Need Instagram app verification for Instagram feed | No | https://prnt.sc/um85s1 https://prnt.sc/um862m
Content Required from client
HGP + GX | About us
HGP + GX | FAQs
HGP + GX | How it works
HGP + GX | Homepage
HGP + GX | Blog
HGP + GX | Shipping info
HGP | Returns
HGP | Terms and conditions
HGP | Privacy Policy
GX | Why Us
GX | Guides
GX | Membership
GX | Support
Social media links
HGP + GX | Facebook
HGP + GX | Twitter
HGP + GX | LinkedIn
HGP + GX | Instagram
End to end test needed in production environment.

## GX and HG Qsheet
| Q | Reference | Answer
PC= Pending Client TD: Pending TD DL: Pending DL
HG | Do you need to be able to edit pricing on the HGP website or will pricing come directly from Hydrofarm? |  | They will offer wholesale price as well as the suggested retail price SRP. We can upload based on the suggested retail price for now and update it when data presents itself latter on? Add this note to spec document dated: 8/4/2020
HG | What is the shipping cost to customers? Free shipping? Is there an order minimum, if so, what amount? |  | yes, free drop shipping at their home. with a minimum purchase order
HG | Once a purchase is made on HGP, do we send an email notification to hydrofarm? How do we notify them? |  | I’m not sure that I understand the question. We don’t need to know when you receive an order – just send the order to us via the API (salesorders/submitOrder). Orders submitted to us will be processed and shipped according to the information sent in the order.
HG | Once we send you an order, we’ll want order tracking info back so that our customers can track their orders. How soon do you typically provide order tracking info? |  | Order tracking information can be gathered by calling the getOrders route. However, order tracking information isn’t available until an order ships and has been invoiced. Orders are typically shipped in 24-48 hours.
HG | Product Detail Page - What is the criteria to display related products? |  | These come from the "related" collection returning from "getProducts"
HG | Product Detail Page - How many related products can be display? |  | After taking a look (and this can change, of course) our largest related group is 16 items, at present.
HG | How far do your categories drilldown to? |  | a. We have two category layers: parent and child b. You can get category information by calling the getCategories route (categories/getcategories).
HG | What product filters do you offer (which appear on the product listing page for users to filter products) |  | a. The getProducts route offers several filter options. These filters are all outlined on the API User Guide (page 9-10).
HG | What product variants to you offer? (size, etc). |  | a. In order to return all product variants, you’ll need to supply the “includeProductVariants” Boolean property (getProducts). Different products offer different variants (many products have no variants at all). Some examples are: i. Size ii. Color iii. Wattage iv. Etc.
HG | Is it possible for one product to be located in multiple categories? |  | a. No, each product will only be in a single category.
HG | I want to avoid running cron jobs to gather product updates. Webhooks would be a more efficient way for us to do this – do you have any thoughts on if we can get that setup? |  | a. This is something that we can explore in the future, but in the short term this will not be available.
HG | Do we have guest checkout in HGP? |  | Nothing like that discussed with the client.
HG | Do website offers sidebar filter? if yes, then what are the side filters? |  | Developer already replied in item #13.
HG | how stock will be managed? who informed hydrofrom that some products are purchased. For example hydrofarm sent us 10 quantities for some products and 2 are sold on our site now how dyrofarm will know the remaining stock is 8 now. Because i dont see any stock information coming in api. |  | You already asked this question on other places on this sheet. Remove.
HG | There's no variant data coming in api we pass the flag includeProductVariants=true but variants data didnt come in api response |  | Are these two questions? or the same qustion asked twice? | These are two different cases | This is working as expected. Can you provide the input that’s not working for you? The following works in my testing: https://api.hydrofarm.com/api/products/getProducts { "includeProductVariants": true }
HG | There's no product coming in developement mode of the api |  | Can you provide the URL that you’re calling along with the input payload? This is working currently. | Please see https://prnt.sc/u2647i | 1. Your screenshot doesn’t show an input, only an access token. The URl is correct for getProducts, but the getProducts route is a POST method. You will need to provide body content in order to query products (even if it is just a blank collection “{}”). | We applied as per your reply, this is what we get in respose: https://prnt.sc/u3femo https://prnt.sc/u3fff9 | "It looks like your account is not properly configured in our development environment. I am getting the same results that you reported, however I see expected results in production. Can you try to query production and see how it goes? I will reach out internally to see what can be done to get your development product catalog configured properly. I will let you know. You may encounter cases where the S3 image is unavailable. We are working on a project right now to round out these gaps. Images should never be referenced directly from Hydrofarm.com. Can you confirm that the majority of images URLs are not resolving to error pages (S3)?" | 1. You and I worked through your development environment issues week before last (resolved) 2. The missing images have now been corrected as well: a. https://s3.amazonaws.com/hydrofarm_pubimages/LGBQM2_1.jpg b. https://s3.amazonaws.com/hydrofarm_pubimages/HLH1001_1.jpg c. https://s3.amazonaws.com/hydrofarm_pubimages/HGTB25WB_1.jpg
HG | Variants are being listed as separte product on hydrofarm website and being grouped by famliy right? |  | That is correct
HG | There's no stock infomartion is coming in api |  | Stock levels are provided in the "inventories" collection (getProducts) | What does this information represents in inventories object https://prnt.sc/tuaj3c | BckpInventLocationId represent the SKU’s backup fulfillment warehouse. However, this value is only valid/applicable for customers with an active backup fulfillment rule (locationFulfillmentRule returning from customers/getCustomer) | How to know the product is in stock or out of stock? | • If the product is in stock in your primary warehouse, then you can consider it to be in stock. To determine the warehouse assigned to your account, review data returned from customers/getCustomer. Your primary warehouse is “55” (New Hudson, MI).
HG | I see there's restrction data coming in api response https://prnt.sc/tr5e9e what does that mean? |  | Many items in our catalog have shipping restrictions. These items cannot be shipped to particular states. The "restrictions" collection outlines those shipping restrictions.
HG | Api's contain extra data otherthan listed on hydrofarm, e-g Do we need this data on our site? https://prnt.sc/tvcg68 |  | The client does not know how to answer this type of a question. We need to show the information thee hydrofarm is showing.
HG | There's no brand api available. Please provide |  | In the “attributes” collection you will find an attribute for “Brand”. The corresponding “value” is the product’s brand. | Okay! We need list of logos for the "Our Brand" landing page, but arrtibutes collection is not providing brand list. is there any method to get separete list of brands? getting brands from attrubtes is costly in terms of resources. DISCUSSED WITH AH. PLEASE PROVIDE NEXT STEPS. | I’m sorry, but there is no API route to deliver brands, outside of the getProducts route. If you’re unable to loop through the catalog to collect brand information, I can send you a spreadsheet with our current active brands along with a zip file of brand logos if that would be helpful. | a. Brand listing is https://docs.google.com/spreadsheets/d/143QIGACY0078WETlfZpYKed_9Knak5KW/edit#gid=649386450 b. I am still working on collecting brand logos When you modify these brands or add others, how will I be notified? a. You won’t be. That is why I recommend using the getProducts route to determine a listing of active brands. | Please send over brand logos. | · Our marketing team is still compiling this collection. I will get it over to you as soon as they are done pulling all of the logos together (there are many).
HG | No flag (Input Fields) is working in get product api e-g Whatever you post in api call, reslut remain the same in api responce https://prnt.sc/tttjyq |  | This is working as designed. Here is a sample: { "keyword":"phb2010", "fields":"sku name related", "includeProductVariants": true }
HG | How product vaianta are being displayed on hydrofarm website? its combining SKU and size from family right? |  | Variants have unique SKUs. They also have unique names. In our family/variant display (dropdown box) we use a combination of the Unit Size and SKU as shorthand.
HG | Provided price API is not giving price of the variant. Is there any other API for variant's price then please provide. |  | Pricing is not supplied in the “family” collection. Returned pricing data is specific to the SKU being reported on only. Variants will need to be queried in order to lookup family member pricing.
HG | i observed on hydrofarm.com that there are different price and specifications for the many variants of the same product. where that data is coming from? |  | I’m not sure I understand this question. It is true that variants within a family typically have different prices from one another (along with other product data). Variants are distinct products. All product data can be retrieved from the getProducts route. Variant data can be returned by specifying "includeProductVariants": true in your request.
HG | Should "distribution center" be displayed in the new website as it is now displayed https://prnt.sc/tvpjr3? |  | Hamda says, NO.
HG | How to get subcategorises images like displayed on hydrofarm website |  | What are you referring to? | I am reffering to this page https://www.hydrofarm.com/Catalog/Lighting-Parent | The catalog image is just the default product image. In the “images” collection, there is a property for “isDefault”. Each product will have one default image. If you’re referring to the category landing pages, those images were created for the website. They’re representative products but not set in stone. You can use whatever you want.
HG | We noticed that not all attributes are showing on product detail page in Specifications section, is there any specfic condition to display attributes in specification. |  | These are from the “Attributes” collection. We do explicitly exclude some attributes from display on Hydrofarm.com. We programmatically exclude the following: • AltSearchTerms • Brand • Clearance • HouseBrand • HousePremium • IsNew • IsPreorder • MixMatchGrp • NewEnable • OMRI • WebTitle We also hide any attributes with a blank “value”.
HG | Related products object: Attribute collection is pulling the following two attributes http://prntscr.com/ty7o87 http://prntscr.com/ty7oqs Please have a look and explain about "Disco, where this info need to be use? |  | a. Disco means “Discontinued”. Note that unless a discontinued item still has inventory available, it cannot be purchased.
HG | There's no option to send tax and discount information in submit order api, how we can sen tax info in submit order api? Is there no discount feature in this site? Do this site required tax charges? |  | • Orders submitted to Hydrofarm will be billed to Home Grown Pros and will reflect contracted prices. Any offered pricing and additional discounts would be between Home Grown Pros and the end user. Hydrofarm will bill our price along with any applicable taxes and freight, but that bill will be charged to Home Grown Pros, not the end user making the purchase. This may be more of a question for our sales team, but I can tell you the prices are not passed across when submitting a sales order via the API route (salesorders/submitOrder). All order pricing is calculated by Hydrofarm on the back end when the order is received. • Note for TD: So basically it seems like we don’t have to send any discount or tax info to Hydrofarm. Correect? We need to just have it stored on our website.
HG | As indicated in submit order API these are required parametres, but we can not provide this information https://prnt.sc/tyz574 What are the next steps |  | • You must provide shipping information, otherwise we will not know where to ship the order. I imagine that Home Grown Pros will be taking advantage of our “dropshipment” option. In that case, the customer’s street address will need to be provided. On the other hand, if we will be shipping to Home Grown Pros directly, then you will need to select the “onFile” option and provide the location ID to which you’d like us to ship the order. Note that your configured onFile locations along with their IDs can be retrieved by reviewing the “getCustomer” route (Customers/getCustomer). • Note for TD: I will ask the client. I think client will be using the hydrofarm dropshipping. Keep this question on the QSheet.
HG | API is not providing sale price, where should we get that? |  | · Product pricing is available in the “price” collection returning from getProducts (products/getProducts). In this collection you will see a WholesalePrice collection as well. In this collection, which is based on volume, there is both a “YourPrice” property as well as a “price” property. “YourPrice” is what you will be charged. If the item is on sale or if an additional discount is being offered, the “Price” property will reflect a different, lower price. This is outlined on page 13 of the Hydrofarm API User Guide. | I don't get this reply. We have received "Is Sale True" in API response please have a look https://prnt.sc/u25g37 what is the slae price in this case? | 2. There is no explicit “sale” price returned by the API. The price that you will pay is always provided in the “yourPrice” property. If the item is on sale, this is the sale price. If the product is not on sale, this is still the price that you will pay. Note that you will not always see a price difference between “price” and “yourPrice”, even if the item is on sale. The reported pricing depends upon how it is setup in our ERP. Sometimes a percentage break is applied, and sometimes the base price is simply updated (in which case, “price” and “yourPrice” will be the same value).
HG | in some cases we have two different values of "YourPrice" https://prnt.sc/u259eh which one is to pick and what is the case where 2 value are displays in API response? |  | 3. “yourPrice” will always be what Home Grown Pros will be charged for the item. The “price” property is only there to compare what you will be charged with the “regular” price. If you want, you can completely disregard the “price” – “yourPrice” is what you will be charged.
HG | Where do I gather this information from? https://prnt.sc/u1m3e8. |  | • The prop 65 flag is a product attribute, being returned in the attributes collection (getProducts). The specific content of the tooltip pictured is not available for retrieval (it is coded into our website).
HG | We will need to be informed once a brand is modified. Extracting the brand information the way that it was provided now would require an enormous amount of time and effort. So, we’ll go ahead and use the excel file, but would need a heads up of any future change. |  | I don’t know what mechanism we would use for alerting you of brand updates or who on the Hydrofarm side would be able to take that up. Maybe someone else on the Hydrofarm team can respond with a less technical offering? Note for TD: I will ask their team to provide that info. Keep this question on the QSheet.
GX | What are the different permission for the following admin roles? GrowMaster GrowPro GroTech What information they can see in their dashboard? |  | HS: No different permissions in this phase. Admin will assigne the title wjile creating account. No different dashboard except the title
GX | How GrowMaster, GrowPro, GroTech will be assign to a customer so that they can provide growlog feedback to his assigned customers. |  | When retailer add customer admin get notified that these customer that needs to be assigned, then admin will assigned a grow master. Grow master will get email that you have been assigned to this customer.
GX | Why customer cannot cancel subscription? What if admin not get the email due to the connection issue, system will changed the customer. |  | no easy cancellation
GX | Why refund needs to be manually processed? | http://prntscr.com/u2q6al | if client wants then we will do that in a separate phase.
GX | Is there any way to redirect to GX site from HG? |  | no restriction we can use that.
GX | Do the customer can see their retailers what info the can see? |  | we can shhow the retailer name but not for now, but may be in fuure we show customer who is his retailer.
GX | Retailers have added some customer (with basic info e.g email) how would that customer could login? our understanding is when a retailer add a customer, an auto generated email will be sent to that customer with a random password? | http://prntscr.com/u4vxrx | Well, I think customer should get an email where they click on a link and they are redirected to a page where they have to create a password for themselves. The email should tell them XYZ retailer has invited you.
HG | API returning us image path like this https://s3.amazonaws.com/hydrofarm_pubimages/LGBQM2_1.jpg, and this path provide us a broken image. but on hydrofarm website the image path is different https://www.hydrofarm.com/DesktopModules/Revindex.Dnn.RevindexStorefront/Portals/0/Gallery/ca9fdd60-6ff6-469b-9dd5-22f419a5e12e.jpg. for some products. |  | It looks like your account is not properly configured in our development environment. I am getting the same results that you reported, however I see expected results in production. Can you try to query production and see how it goes? I will reach out internally to see what can be done to get your development product catalog configured properly. I will let you know. You may encounter cases where the S3 image is unavailable. We are working on a project right now to round out these gaps. Images should never be referenced directly from Hydrofarm.com. Can you confirm that the majority of images URLs are not resolving to error pages (S3)?
HG | Is state restriction also for the HGP products or just for GX? | http://prntscr.com/u5hxuc | state restriction is in API of the product.
GX | Billing/shipping address section is missing http://prntscr.com/u8wbpl. As grow kits needs to be sent to customer so shipping address is needed. |  | will be in checkout
GX | What is this for http://prntscr.com/u8xvpz? are these clickable? is this grow log featureb by admin or this will be display based on recent filling? |  | Instagram feedback
GX | In Homepage video you said there is a function of "Fertility Tracker" i don't find anythhing in document related to this. Please provide info rgarding this fuction. |  | its Grow tracker
GX | How will the system determine the Harvest Date? What happens when a GrowLog reaches its Harvest Date?
GX | What type of screen will user see in order to fill growlog? |  | TD working to so me this flow.
GX | What kind of analytic reports needed for the GX website?
HG | There is no way to pass total order amount to submit order API. we need to pass total order amount to charged tax or discount. Please advice further how to pass total order amount .
HG | Difference between get order and get invoice API? |  | 1. getOrders returns order information based on status (Open order data can be returned, etc.). getInvoices will only return invoiced orders. The data returned by both routes is not the same either (different properties are provided).
HG | In Development environment, get order and invoice API is not working. |  | 2. You likely have no orders or invoices in development. The routes are working but there is no data to be retrieved.
GX | Under the subscription plan, the features will be dynamic or static ( one time addition) P.S: subscription feature refers offers that Growx Provide within a particular subscription. E.g. see MailChimp offer under their subscription http://prntscr.com/ufh1b5. | http://prntscr.com/ufh1b5 | Features are not dynamic. They are static.
HG | we have submitted orders to hydrofarm and got these refrence numbers for 2 orders 7336_14029_200907_232352541 7336_14029_200907_230221043 Can you send dummy tracking info for these two orders? Also currently im seeing order status as open when that staus will change and how that will be changed? |  | Answered on TW.
HG | Please add the flow of growlog and how GrowMaster, GrowTec, and GrowPro will provide feedback to the Growlog |  | will be done in chat
HG | how admin set grow tracker to appear in customers dashboard? |  | Admin will upadate the weekly milestones (videos/Sides) in the admin panel for customers's GrowTracker. System will provide the video/slides of the related week. e.g once week one get completes the user will have the milestone of the second week
GX | There will be one subscription or there will be three or more like MailChimp? | http://prntscr.com/ufh1b5 | 1. You can subscribe monthly or anually. And then you have to select a kit size.